## TestPlan
Test Planner and Tracker |  |  | 45 | Anushka Sinha, Ayush Agarwal, Yashav Bhatanagar, Naveen Kumar Medam, Masthan Sharif Shaik
Test No. ID | Related Use case | Pre-conditions | Test Description (steps) | Expected Outcome | R1 Outcome (color code cell background) | Comments (if test case failed) | R2 Outcome (color code cell background) | Comments (if test case failed)
1 | UC-01: Local Knowledge Graph Creation (R1) | Wazuh agents are active and reporting telemetry | 1. Trigger the Node Agent to connect to the Wazuh API. 2. Retrieve asset and vulnerability data from Wazuh. 3. Normalize and map the data to the ORBIT schema. | The Node Agent successfully retrieves the raw telemetry and outputs normalized JSON (ready for Neo4j update). |  |  | NA
2 | UC-04: Inject Action Card into Wazuh (R1) | Action Card received from ORBIT Core | 1. Pass a dummy Action Card to the Node Agent. 2. Validate the Action Card. 3. Translate it to Wazuh format. 4. Inject it into Wazuh as an alert. | The Action Card is successfully translated and appears as a visible alert to the analyst in the Wazuh console |  |  | NA |  | Fail
3 | UC-05: Human-in-the-Loop Execution (R1) | ORBIT alert is visible in Wazuh (Test 2 completed) | 1. Log in as SOC Analyst. 2. Review the injected alert in the Wazuh UI. 3. Approve the execution. 4. Trigger the Wazuh Active Response mechanism | The action is executed using Active Response, and the approval decision is successfully recorded |  |  | NA |  | Pass
4 | UC-06: Pending Action Assignment (R1) | Action pending resolution in Wazuh | 1. Locate an unresolved action alert in the Wazuh console. 2. Leverage Wazuh's native workflow/ticketing functionality to assign the pending action to a specific analyst. 3. Track its status. | The pending action is successfully assigned using Wazuh's internal workflow and its status is tracked until resolution. |  |  | NA |  | Partial / needs fixing
5 | UC-05: Human-in-the-Loop Execution (R2) | Node Agent has prepared Asset Inventory and Crown Jewel data. | 1. Access the HITL interface. 2. Prompt the SOC Analyst to review the Crown Jewel assignment (Yes/No). 3. Prompt the Analyst to review the Asset Inventory subscription (Yes/No). 4. Submit the confirmation. | Analyst confirmations (Yes/No) for Crown Jewel assignment and Asset Subscription are successfully captured before being sent to the Core. | NA |  |  |  | Not tested
6 | UC-08: Completion Feedback (R2) | Action executed in Wazuh via Active Response (Test 3 completed) | 1.Node Agent queries Wazuh (the actor) to retrieve the final completion status of the executed action. 2. Capture the execution result and metadata (excluding sensitive raw data). 3. Format payload for the Core | Wazuh successfully reports the completion status, which is captured by the Node Agent to update the local graph and notify the Core | NA
7 | Exception Handling (Applies to UC-01 & UC-03) | Wazuh Manager is temporarily offline or unreachable | 1. Trigger the Node Agent to retrieve telemetry or feedback. 2. Observe the system response. | The script handles the error gracefully, logs the failure, and queues a retry later without crashing the Node Agent
8 | UC-02: To verify that presidio is running: | Docker Desktop running docker-compose.yml configured Port 5001 exposed | 1.Open terminal. 2.Navigate to project root: cd ~/presidio-local 3.Run: docker ps 4.Verify container named presidio-analyzer is listed. 5.Run: curl http://localhost:5001/health | Container appears in docker ps curl returns: Presidio Analyzer service is up HTTP status code 200 |  |  | NA
9 | UC-02: Detect an email address: | Presidio container running scan_request_chunks.jsonl exists in data/request | 1.Open data/request/scan_request_chunks.jsonl 2.Add a test line: {"chunk_id":"test_email_1","asset_id":"A1","content_text":"email: test.user@example.com"} 3.Save file. 4.Run: python3 scripts/analyze_chunks.py5. 5.Open: data/result/scan_result_chunks.jsonl 6.Search for test_email_1. | Output contains: "entity_type": "EMAIL_ADDRESS" Confidence score ≥ 0.8 chunk_id matches input Pass criteria: Entity Exists Fail criteria: presidio_entities empty |  |  | NA
10 | UC-02: Detect Credit card number: | Presidio Running | 1.Add:{"chunk_id":"test_card_1","asset_id":"A2","content_text":"card number 4716190207394368"} 2. Save file. 3. Run: python3 scripts/analyze_chunks.py5. 4. Open: data/result/scan_result_chunks.jsonl 5. Search for test_card_1. | Entity type = CREDIT_CARD Correct start and end positions Score ≥ 0.6 Pass criteria: CREDIT_CARD detetcted Fail criteria: No Detection OR wrong entity |  |  | NA
11 | UC-02: Detect Phone Number: | Presidio Running | 1.Add:{"chunk_id":"test_phone1","asset_id":"A3","content_text":"Contact: 9876543210"} 2. Save file. 3. Run: python3 scripts/analyze_chunks.py5. 4. Open: data/result/scan_result_chunks.jsonl 5. Search for test_phone_1. | PHONE_NUMBER entity detected Confidence ≥ 0.7 Pass Criteria: PHONE_NUMBER present. Fail Criteria: Entity missing or misclassified. |  |  | NA
12 | UC-02: Detect Person Name | Presidio Running | 1.Add:{"chunk_id":"test_person_1","asset_id":"A4","content_text":"Customer Name: Rahul Sharma"} 2. Save file. 3. Run: python3 scripts/analyze_chunks.py5. 4. Open: data/result/scan_result_chunks.jsonl 5. Search for test_person_1. | PERSON entity detected Confidence ≥ 0.7 Pass Criteria: PERSON present. Fail Criteria: Entity missing or misclassified. |  |  | NA
13 | UC-02: Handling enpty content_text | Docker Desktop running Presidio container running (docker ps confirms) analyze_chunks.py contains null/empty string handling logic data/request/scan_request_chunks.jsonl exists data/result/ directory exists and is writable | 1.Open terminal. 2.Navigate to project root: cd ~/presidio-local 3.Open input file: nano data/request/scan_request_chunks.jsonl 4. Add the following line: {"chunk_id":"test_empty_1","asset_id":"A6","content_text":""} 5.Save and exit. 6. Run the analysis script: python3 scripts/analyze_chunks.py 7.Wait for execution to complete. 8.Open output file: nano data/result/scan_result_chunks.jsonl 9.Search for:test_empty_1 | Script execution completes without exception: No crash or traceback error displayed. Output contains: "presidio_entities": [] chunk_id correctly preserved. Pass Criteria: No runtime error. Entities list is empty. Fail Criteria: Script crashes. Python traceback displayed. Output missing or malformed. |  |  | NA
14 | UC-02: Handling missing content_text | Presidio container running Script includes safe dictionary access (.get() instead of direct key reference) Input and output folders existC10:C11 | 1.Open: data/request/scan_request_chunks.jsonl 2.Add: {"chunk_id":"test_missing_1","asset_id":"A7"} 3.Save file. 4.Run: python3 scripts/analyze_chunks.py 4.Observe terminal output. 5.Open result file. 6.Search for test_missing_1 | Script does not throw KeyError. Execution completes normally. presidio_entities = [] Once logging implemented → error message logged. Pass Criteria: Graceful handling with no crash. Fail Criteria: KeyError or termination. |  |  | NA
15 | UC-02: Handling Service Unavailability (Presidio Offline) | Script configured to catch HTTP errors Presidio container currently running | 1.Stop Presidio:.docker stop presidio-analyzer 2..Confirm container stopped: docker ps 3.Run analysis script: python3 scripts/analyze_chunks.py 4.Observe terminal output. 5.Check if result file created or partially written. | Expected Outcome: HTTPError caught. Clear error message displayed: Connection refused or service unavailable Script exits gracefully. No corrupted JSON output file. Pass Criteria: No abrupt crash; controlled failure. Fail Criteria: Unhandled exception; stack trace shown. |  |  | NA
16 | UC-02: Large file performance test | System has ≥4GB RAM Presidio running Base input file exists | 1.Duplicate test input to >1000 lines: 2.for i in {1..1000}; do cat sample.jsonl >> scan_request_chunks.jsonl; done 3.Run performance test: time python3 scripts/analyze_chunks.py 4.Observe execution time. 5.Verify memory usage using: top 6.Count input lines: wc -l data/request/scan_request_chunks.jsonl 7.Count output lines: wc -l data/result/scan_result_chunks.jsonl | Script completes execution. No memory overflow. Output line count equals input line count. Execution time reasonable (< 2 minutes for 1000 lines). Pass Criteria: No crash and counts match. Fail Criteria: Memory error or mismatch in lines. |  |  | NA
17 | UC-02: Multiple Sensitive Fields Same Asset | Aggregation logic implemented Threshold defined in config Presidio running | 1.Add three entries: {"chunk_id":"c1","asset_id":"AS1","content_text":"email: a@test.com"} {"chunk_id":"c2","asset_id":"AS1","content_text":"card 4716190207394368"} {"chunk_id":"c3","asset_id":"AS1","content_text":"Contact: 9876543210"} 2.Run script. 3.Trigger aggregation module. 4.Inspect final classification output. 5.Locate asset_id AS1. | 3 entity types detected. Sensitivity score exceeds threshold. (To be decided) Crown_Jewel = TRUE. Pass Criteria: Asset flagged TRUE. Fail Criteria: Flag FALSE despite multiple sensitive fields. |  |  | NA
18 | UC-02: Single Low Sensitivity Field | Presidio running, aggregation threshold defined in config. | 1.Open scan_request_chunks.jsonl. 2.Add a single entry with low-sensitivity data: {"chunk_id":"c4","asset_id":"AS2","content_text":"Name: John Doe"}. 3.Run python3 scripts/analyze_chunks.py. 4.Inspect final classification output for asset AS2. | PERSON entity detected, but sensitivity score remains below the threshold. Crown_Jewel = FALSE. Pass Criteria: Asset is correctly flagged as FALSE. Fail Criteria: Asset is incorrectly flagged as a Crown Jewel. |  |  | NA
19 | UC-03: Generate and Send Optimized Subscription | Knowledge graph has mapped an asset with a Presidio sensitivity score. | 1. Trigger the Node Agent to analyze local context. 2. Generate the subscription summary payload. 3. Send to the ORBIT Core stub/API. | Payload successfully transmits to the Core containing only anonymized/optimized metadata (no raw sensitive text is leaked). |  |  | NA
20 | UC-07: Differential Updates (Main Flow) | Local context changed (e.g., a new asset added, or a vulnerability patched) | 1. Trigger the Node Agent to detect changes. 2. Package the deltas (incremental changes). 3. Send the update to the Core. | Only deltas are transmitted to the Core to reduce data volume and preserve privacy. Core context is successfully synchronized. | NA
21 | UC-07: Differential Updates (Alternate Flow) | ORBIT Core is temporarily unavailable (e.g., network disconnected). | 1. Trigger the Node Agent to send a differential update. 2. Observe local system behavior. | Differential updates are cached locally without error and successfully synchronized when connectivity is restored. | NA
22 | UC-08: Completion Feedback (Main Flow) | An action has been executed via Wazuh (from R1 scope). | 1. Capture the execution result. 2. Update the local knowledge graph. 3. Notify the Core. | The Core successfully receives execution feedback (status and relevant metadata) to enable learning, strictly excluding any sensitive raw data | NA
23 | UC-08: Completion Feedback (Alternate Flow) | Feedback delivery to the ORBIT Core fails (e.g., API timeout). | 1. Attempt to send completion feedback while the network is down. 2. Restore the network connection | Execution results are retained locally without crashing and are transmitted successfully when connectivity is restored. | NA
24 | UC-01: Local Knowledge Graph Creation (Main Flow) | The Neo4j database is populated with assets, vulnerabilities, and threats | 1. Open Neo4j Bloom. 2. Load the custom "Semantic Bloom Perspective" template. 3. Execute a Cypher visualization query to map an asset to a threat. | The analyst can successfully traverse asset-to-threat relationships visually. Nodes and edges are displayed correctly according to the ORBIT ontology. |  |  | NA
25 | UC-02: Privacy Scan & Crown Jewel ID (Main Flow) | Presidio has assigned sensitivity scores and flagged certain assets in the graph as Crown Jewels | 1. Open Neo4j Bloom. 2. Run the Cypher query for "Crown Jewel classification". 3. Observe the visual output. | Crown Jewel assets and their sensitivity relationships are visually distinct and identifiable on the graph canvas |  |  | NA
26 | UC-05: HITL Execution (Main Flow) | The Node Agent has generated a prioritization output/action card pending human review | 1. Open NeoDash. 2. Load the "Intelligence Dashboard". 3. Navigate to the "Top Risky Assets" or "Prioritization Context" view | The dashboard successfully loads real-time risk metrics and visually explains why the Node Agent prioritized a specific action, supporting the analyst's validation workflow. |  |  | NA
27 | UC-05: HITL Execution (Alternate Flow / Missing Data) | A threat exists, but specific vulnerability metadata is missing from the graph for a particular asset. | 1. Open NeoDash. 2. Load the Intelligence Dashboard for the affected asset. | The dashboard renders gracefully without crashing, displaying the available context (e.g., asset topology) and handling the missing metadata cleanly. |  |  | NA
28 | Privacy / Constraint Check: (Applies to all) | NeoDash and Bloom are connected to the live local Knowledge Graph containing Presidio data. | 1. Navigate through all NeoDash views and Bloom perspectives. 2. Inspect the data attributes displayed on the screen. | Crucial Pass Criteria: Visualizations strictly respect anonymization. There is absolutely NO exposure of sensitive raw data on the dashboards |  |  | NA
29 | UC-07: Differential Updates (Main Flow) | A baseline graph exists. The environment changes (e.g., a vulnerability is patched), and the ORC updates the graph | 1. Keep the NeoDash Intelligence Dashboard open. 2. Wait for the ORC to process a differential update in the background. 3. Refresh/observe the dashboard. | The visualizations automatically update to reflect the new graph state (e.g., the patched asset is no longer flagged as high risk) without requiring UI code changes. | NA
30 | UC-01: Local Knowledge Graph Creation (Main Flow) | Wazuh manager running with simulated active agents. Neo4j database is completely empty. ORC configured with Wazuh API credentials. | 1. Start the ORC Docker container. 2. Trigger the ORC's initial asset ingestion script via CLI/API. 3. Open Neo4j Browser. 4. Execute Cypher query: `MATCH (a:Asset) RETURN a`. | 1. Neo4j returns exactly the number of active Asset nodes reported by Wazuh. 2. Node properties explicitly contain OS versions, IP addresses, and agent IDs. 3. No errors in ORC logs. |  |  | NA
31 | UC-01: Local Knowledge Graph Creation (Alternate Flow - Empty State) | Wazuh manager is running but has 0 active connected agents. Neo4j is empty. | 1. Start the ORC Docker container. 2. Trigger the ORC's initial asset ingestion script. 3. Monitor the ORC console logs. 4. Query Neo4j: `MATCH (n) RETURN n`. | 1. ORC console logs an informational message indicating 0 active assets found in Wazuh. 2. ORC does not crash. 3. Neo4j remains empty (0 nodes returned). |  |  | NA
32 | UC-02: Privacy Scan & Crown Jewel ID (Integration) | Presidio container is running. A test database is populated with dummy PII. ORC is connected to Presidio via API. | 1. Trigger the ORC's privacy scan routine targeting the test database. 2. Wait 10 seconds. 3. Open Neo4j Browser. 4. Execute query: `MATCH (a:Asset) RETURN a.CrownJewel, a.SensitivityScore`. | 1. Query returns `a.CrownJewel = True` for the test database. 2. Query returns `a.SensitivityScore` greater than the defined threshold. |  |  | NA
33 | UC-03: Subscription Sync (Privacy Check) | Neo4j graph is populated. Dummy Core mock server is running and listening for POST requests on localhost. | 1. Trigger the ORC's 'Core Sync' function. 2. Open Dummy Core logs to intercept the HTTP POST request. 3. Inspect the raw JSON body payload. | 1. Payload received by Dummy Core (HTTP 200). 2. JSON payload contains anonymized data. 3. Payload MUST NOT contain IP addresses, hostnames, or specific vulnerability details. |  |  | NA
34 | UC-04: Inject Action Card into Wazuh (Main Flow) | Wazuh API is active. Dummy Core mock server is running. | 1. From the Dummy Core, send a valid JSON Action Card payload to the ORC webhook. 2. Wait 5 seconds. 3. Log into the Wazuh Dashboard UI. 4. Navigate to Alerts/Incidents. | 1. ORC returns HTTP 200 OK. 2. A new alert titled 'Pending Assignment' appears in the Wazuh UI with mitigation steps matching the Core's JSON payload. |  |  | NA
35 | UC-04: Inject Action Card into Wazuh (Alternate Flow - Bad Input) | Wazuh API is active. Dummy Core mock server is running. | 1. Open Postman. 2. Send a deliberately corrupted JSON payload (missing required 'target_asset' field) to the ORC webhook. 3. Check ORC application logs and Wazuh UI. | 1. ORC returns HTTP 400 Bad Request. 2. ORC logs an explicit 'JSON Parsing Error' message. 3. ORC does NOT crash. 4. No ghost alert is created in Wazuh. |  |  | NA
36 | UC-05 & UC-06: Human-in-the-Loop Execution (Approve) | UC-04 is complete. 'Pending Assignment' alert is visible in the Wazuh UI. | 1. In Wazuh Dashboard, select the 'Pending Assignment' alert. 2. Change the alert status to 'Approved'. 3. Wait for ORC polling cycle. 4. Query Neo4j: `MATCH (act:ActionCard) RETURN act.status`. | 1. Neo4j query returns `act.status = 'Mitigated'`. 2. ORC logs indicate the state change was successfully detected. |  |  | NA
37 | UC-07: Differential Updates (Delta Check) | UC-03 is complete (Initial sync done). | 1. Register 1 new dummy agent in Wazuh with a specific software package. 2. Trigger ORC's differential update cycle. 3. Intercept the request at the Dummy Core mock server. | 1. JSON payload contains ONLY the metadata for the newly added agent. 2. The payload MUST NOT contain the full metadata of the original agents synced in Test 31. |  |  | NA
38 | UC-08: Completion Feedback (Metrics Sync) | UC-05 is complete (Action marked Mitigated). Dummy Core is listening. | 1. Trigger ORC's completion feedback cycle. 2. Intercept the network request at the Dummy Core. 3. Inspect the JSON body payload. | 1. Payload contains the original Action ID and `success: true`. 2. Payload contains calculated `time_to_mitigate` metrics. 3. Payload contains NO sensitive raw logs. |  |  | NA
39 | Exception Handling: Presidio Offline | Test database has PII. Presidio Docker container is MANUALLY STOPPED. | 1. Trigger ORC's privacy scan routine. 2. Monitor ORC console logs. 3. Query Neo4j for the target asset. | 1. ORC logs a 'Connection Timeout' exception. 2. ORC handles the error gracefully without a fatal crash. 3. Neo4j asset node property `ScanStatus` is updated to 'Pending_Retry'. |  |  | NA
40 | Exception Handling: Core Offline | Dummy Core API is MANUALLY STOPPED. | 1. Trigger a differential update (UC-07) or completion feedback (UC-08). 2. Observe ORC logs. 3. Bring Core back online. | 1. ORC gracefully handles the timeout and caches the payload locally. 2. ORC successfully transmits the cached payload once the Core is back online. |  |  | NA
41 | R2 - Agentic Brain: MCP Prioritization | Neo4j contains one asset tagged 'CrownJewel: True' and one 'CrownJewel: False'. MCP Agent is enabled in ORC. | 1. From the Dummy Core, broadcast a generic Threat Intel feed applicable to both assets. 2. Allow MCP to process. 3. Open Wazuh Dashboard and inspect generated Action Cards. | 1. The Action Card injected for the Crown Jewel asset is assigned a 'CRITICAL' severity. 2. The Action Card for the non-Crown Jewel asset is assigned a lower severity. | NA
42 | UC-01: Create Asset node from Wazuh payload(Main-Flow) | Empty graph; valid Wazuh asset payload available | 1. Send asset payload 2. Trigger ingestion 3. Query Neo4j | Asset node created with unique asset_id and properties populated |  |  | NA
43 | UC-01: Prevent duplicate Asset creation (idempotency)(Edge) | Asset already exists | 1. Send identical payload 2. Query node count | No duplicate node created; properties updated if changed |  |  | NA
44 | UC-01: Create Vulnerability relationship(Main-Flow) | Asset exists; vulnerability payload received | 1. Ingest vulnerability 2. Match Asset 3. Verify relationship | (:Asset)-[:HAS_VULNERABILITY]->(:Vulnerability) created |  |  | NA
45 | UC-01: Wazuh unavailable handling(Alternate-Flow) | Wazuh service down | 1. Trigger ingestion 2. Check graph state | No partial graph updates; previous state preserved |  |  | NA
46 | UC-02: Store sensitivity score for DataAsset(Main-Flow) | Presidio output available | 1. Send sensitivity score 2. Update graph 3. Query DataAsset | Sensitivity property stored; classification label applied |  |  | NA
47 | UC-02: Mark Asset as Crown Jewel(Main-Flow) | Sensitivity score above threshold | 1. Run classification logic 2. Query Asset node | Asset.crown_jewel = true |  |  | NA
48 | UC-02: Inaccessible scan target handling(Alternate-Flow) | Scan target inaccessible | 1. Attempt update 2. Check logs 3. Query graph | No sensitivity node created; failure logged |  |  | NA
49 | UC-03: Generate subscription summary from graph (Main-Flow) | Knowledge graph populated | 1. Run subscription query 2. Validate output | Subscription node created/updated with context summary |  |  | NA
50 | UC-03: Core unreachable during subscription(Alternate-Flow) | Core API unavailable | 1. Generate subscription 2. Attempt send 3. Check graph | Subscription stored locally with status=queued |  |  | NA
51 | UC-04: Store valid ActionCard in graph(Main-Flow) | Valid ActionCard received | 1. Validate payload 2. Create ActionCard node | ActionCard node created with status=received |  |  | NA
52 | UC-04: Reject invalid ActionCard(Alternate-Flow) | Malformed payload received | 1. Attempt ingestion 2. Query graph | No ActionCard node created; error logged |  |  | NA
53 | UC-05: Approve action and update status(Main-Flow) | ActionCard exists; Analyst approves | 1. Update status 2. Query graph | ActionCard.status = approved; execution timestamp stored |  |  | NA
54 | UC-05: Reject action and record decision(Alternate-Flow) | ActionCard exists; Analyst rejects | 1. Update status 2. Query graph | ActionCard.status = rejected; reason stored |  |  | NA
55 | UC-06: Create PendingAction node(Main-Flow) | Action cannot be executed immediately | 1. Create PendingAction 2. Link to Analyst | (:PendingAction)-[:ASSIGNED_TO]->(:Analyst) created |  |  | NA
56 | UC-06: Track status transitions(Main-Flow) | PendingAction exists | 1. Update status from open → in-progress → resolved | Status transitions correctly persisted |  |  | NA
57 | UC-07: Detect asset property change(Main-Flow) | Asset exists; property modified | 1. Modify property 2. Trigger delta 3. Query DeltaEvent | DeltaEvent node created with change metadata | NA
58 | UC-07: No delta when no changes(Edge) | No graph changes | 1. Trigger delta process 2. Check results | No DeltaEvent created | NA
59 | UC-07: Core unavailable during delta send(Alternate-Flow) | DeltaEvent created; Core down | 1. Attempt send 2. Check graph | DeltaEvent.status=queued | NA
60 | UC-08: Update ActionCard after execution(Main-Flow) | Action executed | 1. Capture result 2. Update node | ActionCard.status=completed; result metadata stored | NA
61 | UC-08: Retain feedback when Core unavailable(Alternate-Flow) | Execution complete; Core down | 1. Attempt send 2. Query graph | Feedback stored locally with status=pending_sync | NA
62 | ALL: Enforce unique Asset ID constraint(Edge) | Constraint defined | 1. Attempt duplicate create | Database rejects duplicate with constraint error |  |  | NA
63 | ALL: Orphan vulnerability prevention(Edge) | Vulnerability payload without asset | 1. Attempt ingestion | Vulnerability not created without linked Asset |  |  | NA
64 | ALL: Large dataset ingestion(Edge) | 10k assets payload | 1. Bulk ingest 2. Measure time | Graph update within acceptable latency threshold |  |  | NA
65
66
67

## Instructions
Test plan Instructions
It is particularly important that you create a substantial set of Acceptance
Tests. These are tests based on the requirements document. Each acceptance
test should describe an operation to be performed by the user, and the
expected outcomes from that operation. The objective is to define a
comprehensive set of tests that between them cover all the features in the
requirements document. The tests should preferably cover all the frequent
"normal use" scenarios, as well as commonly occurring exception scenarios.
Each acceptance test must be described as a set of user instructions for
performing the test, much like a user manual. The outcomes description
specifies how the user knows whether the test succeeded or failed. The
reason for defining acceptance tests early in the life-cycle is to
facilitate "test-driven development". Developers can look at the acceptance
tests that their module must satisfy, and thereby know exactly what behavior
is expected from their module. Make sure to update these if/when
requirements change. Make sure to follow the suggested format.

## Monopoly Example
Monopoly Test Planner and Tracker (example)
Game in test mode implies that the tester can control the outcome of the dice roll - assume dice roll can exceed 12 for testing.
Note that some of the test cases require previous test cases to be completed as a precondition.
Acceptance tests
Test No. | User Story covered | Preconditions | Test Description | Expected Outcome | R1 Outcome | R2 Outcome
1 | Move Player | Game is in test mode. Game is in initial state. Number of Players: 1 Player 1 Name: Tester1 | Player 1 Dice Roll Total : 5 Player 1 End Turn | Player 1 is located at Reading Railroad cell.
2 | Move Player | Test 1 completed | Player 1 Dice Roll Total : 5 Player 1 End Turn | Player 1 is located on Jail cell.
3 | Move Players in Turns | Game is in test mode. Game is in initial state. Number of Players: 2 Player 1 Name: Tester1 Player 2 Name: Tester2 | Player 1 Dice Roll: 5 Player 1 End Turn | Player 1 is located at Reading Railroad
|  |  | Player 2 Dice Roll: 3 Player 2 End Turn | Player 2 is located at Baltic Avenue
4 | Pass Go | Game is in test mode. Game is in initial state. Number of Players: 1 Player 1 Name: Tester 1 | Player 1 Dice Roll: 39 Player 1 End Turn | Player 1 is located at Boardwalk
|  |  | Verify Player 1 bank balance | Player 1 has $1500
5 | Pass Go | Game is in test mode Game is in initial state. Number of Players: 1 Player 1 Name: Tester 1 | Player 1 Dice Roll: 40 Player 1 End Turn | Player 1 is located on GO cell
|  |  | Verify Player 1 bank balance | Player 1 has $1700 | Go money paid out only after passing GO, not when it is reached.
6 | Pass Go | Game is in test mode. Game is in initial state. Number of Players: 1 Player 1 Name: Tester 1 | Player 1 Dice Roll: 41 Player 1 End Turn | Player 1 is located at Mediterranean Avenue
|  |  | Verify Player 1 bank balance | Player 1 has $1700