# Scope Management Plan — ORBIT NODE (Neo4j Schema & Implementation)

Prepared by: Yashav Bhatnagar

## 1. Purpose

Provide a concise, high-level statement of what the Neo4j schema & implementation effort will deliver for the ORBIT NODE and how the team will manage that scope.

Objective: deliver a privacy-aware, production-ready knowledge-graph model (Neo4j) for Node responsibilities — asset inventory, vulnerability & sensitivity metadata, ActionCard lifecycle, simple prioritization and delta exports for Core — while keeping the interface clear for integrators.

## 2. Scope Summary (high level)

| In scope | Out of scope |
| --- | --- |
| Design of the property-graph ontology (labels, relationships, key properties) | Building Core services or Core-side ingestion/consumption logic |
| Database rules and structure needed to safely build and maintain the Neo4j graph. | Full Node Agent runtime/application code (only templates and contracts provided) |
| Ingestion mapping templates (conceptual Cypher patterns) and delta/export contract design | Presidio model training/tuning, Wazuh agent ops, or UI dashboards |
| ActionCard representation and lifecycle (graph-level) | Hosting procurement, production infra provisioning |
| Privacy-by-design rules (PII minimization, anonymized exports) | Long-term PII storage or vault operation |

## 3. Key Deliverables (summary table)

| ID | Deliverable (high level) |
| --- | --- |
| D1 | Graph ontology & data dictionary (conceptual model) |
| D2 | Schema guidance (constraints/index patterns + versioning approach) |
| D3 | Integration contracts (ActionCard & delta payload examples) |
| D4 | Ingestion templates (conceptual, idempotent patterns) |
| D5 | Priority / scoring approach (conceptual & usage notes) |
| D6 | Migration & minimal ops checklist (high level) |
| D7 | Documentation package (overview docs + handover notes) |

## 4. Roles & Responsibilities

### 4.1 Internal Module Team (ORBIT NODE)- Yashav Bhatnagar

| Role | Responsibility (summary) |
| --- | --- |
| Neo4j Schema | Owns the graph model, writes the schema guidance and mapping templates, authors migration notes and documentation. |
| Integrator / Node Agent Developer | Uses provided templates/contracts to implement ingestion and delta/exports; handles retries/batching in application code. |
| Security Contributor | Validates PII minimization approach and approves anonymization/ hashing rules. |
| Analytics Contributor | Defines high-level priority/scoring logic and advises on when to use GDS for heavier analytics. |

### 4.2 External Integration Stakeholders

| Stakeholder | Responsibility (summary) | Owner |
| --- | --- | --- |
| Core Team | Agree on ActionCard/delta contract and consume Node exports. | Core Team |
| Presidio / Data Classification | Provide sensitivity outputs and normalization guidance. | Anushka |
| Wazuh / Telemetry Team | Provide telemetry formats and canonical identifiers for hosts/assets. | Sharif |
| DevOps / Infrastructure | Provision Neo4j staging/production environment and ensure plugin availability (APOC/GDS) if required. | Ayush |

## 5. High-Level Timeline (phases)

| Phase | Goal (deliverable focus) | Typical duration |
| --- | --- | --- |
| Phase 1 — Model & Contracts | Deliver D1, D3 (ontology + contracts) | 23rd Feb |
| Phase 2 — Schema Guidance | Deliver D2, D4 (schema guidance + templates) | 4th March |
| Phase 3 — Priority & Ops | Deliver D5, D6 (priority approach + ops checklist) | 10th March |
| Phase 4 — Documentation & Handover | Deliver D7; coordinate integrations | 16th March |

## 6. High-Level Risks & Mitigations

| Risk | Impact | Mitigation (brief) |
| --- | --- | --- |
| PII handling mistakes | Critical | Enforce privacy-by-design: only store hashed/pseudonymized identifiers; Security contributor sign-off. |
| Overly complex model causing performance issues | Medium | Keep model focused on required queries; recommend using GDS only for heavy analytics. |
| Single implementer capacity | Medium | Prioritize D1–D3 first; provide clear, small templates to reduce integrator effort. |

## 7. Constraints & Assumptions

- Node provides graph-level artifacts; application-level ingestion and infra are delivered by integrators/DevOps.

- Presidio outputs are treated as metadata; raw PII is not persisted in Neo4j.

- Core will review and accept the ActionCard & delta contract before full integration.

## 8. Acceptance Criteria

A high-level handoff is complete when:

- Core has approved the ActionCard & delta contract examples.

- The ontology & schema guidance is published and reviewed by Security contributor.

- Integrators have what they need (templates + documentation) to implement ingestion and exports.